## 0. Document Control
VEHICLE BEHAVIORAL MODEL
Requirements & Verification Specification (MIL / SIL / PIL / HIL)
Model-Based Design Verification Plan — dSPACE SCALEXIO Program
Document ID | MBD-VBM-RVS-001
Model Baseline | VehicalBehavioralModeling/Matlab/Veh_Behavior_Modeling_Exp1.slx
Source Repository | thippeswammy/MBD-dSPACE
Derivation Method | Reverse-engineered directly from .slx block-diagram XML + Stateflow chart (ground truth), cross-checked against repo README
Document Status | DRAFT — pending Open Decisions sign-off (see Sheet 7)
Revision | v2.0
Classification | Internal / Engineering Use
REVISION HISTORY
Rev | Date | Author | Description of Change
v0.1 | — | Engineering (Claude-assisted trace) | Initial draft derived from README only; multiple items marked TBD pending model inspection.
v1.0 | — | Engineering (Claude-assisted trace) | Full .slx block-diagram trace completed; all TBDs closed; 4 defects and 3 documentation discrepancies identified.
v2.0 | — | Engineering (Claude-assisted trace) | Restructured to industry format: explicit Input/Expected-Output fields per requirement; dedicated MIL/SIL/PIL/HIL test specifications with stage-specific interface and environment definitions; safety classification added.
HOW TO READ THIS WORKBOOK
Sheet 1 — Requirements | The single source of truth. Every requirement states, explicitly, the INPUT signal(s)/condition(s) that must be supplied and the EXPECTED OUTPUT that must result. All downstream test sheets trace back to a REQ-ID here.
Sheets 2-5 — MIL / SIL / PIL / HIL Test Specifications | Each stage tests the SAME requirements, but the meaning of 'input' and 'expected output' changes: MIL = model signals in Simulink; SIL = the same values fed to host-compiled generated code; PIL = the same values delivered over a real interface (CAN/serial) to a target processor; HIL = the same values delivered as real electrical signals to the SCALEXIO real-time target, with physically measured outputs. Each sheet states the interface, tools, and pass criteria specific to that stage.
Sheet 6 — Traceability Matrix | REQ-ID x Test-ID cross-reference across all four stages, with roll-up status.
Sheet 7 — Open Decisions | Items where the model and the documentation disagree. These MUST be resolved and signed off before Sheet 1 requirements are considered LOCKED / BASELINED.
Sheet 8 — HW Integration Targets | Maps Raspberry Pi / Arduino / Jetson AGX Orin / Jetson Thor / SCALEXIO LabBox / MicroAutoBox III onto the MIL-SIL-PIL-HIL chain for this specific project.

## 1. Requirements
REQ-ID | Category | Subsystem / Block Path | Requirement (Shall Statement) | REQUIRED INPUT (signal, range, condition) | EXPECTED OUTPUT (signal, value/range) | As-Built Formula (traced from .slx) | Priority | Safety Class | Verif. MIL | Verif. SIL | Verif. PIL | Verif. HIL | Status | Notes / Discrepancy
REQ-SW-010 | Ignition | Root / system_652 | The system shall drive Car ON/OFF LED directly from the Car ON/OFF input with no filtering. | CarON/OFF (digital) = 0 or 1 | Car ON/OFF LED (digital) = same value as input, same simulation step | LED = CarON/OFF (direct passthrough) | Medium | B | Y | Y | Y | Y | CONFIRMED
REQ-SW-011 | Ignition / Safety Interlock | Gear Box, system_729 | WHEN Car ON/OFF = 0, the system shall force the Gear output to Neutral (0), overriding the Car Gears input. | CarON/OFF = 0; CarGears = any value 0-1023 (including values that would select Reverse or Forward if ignition were on) | Gear = 0 (Neutral), regardless of CarGears value | MultiportSwitch control = 1 + CarON/OFF*ROUND(CarGears/511.5); CarON/OFF=0 forces control=1 -> selects Neutral | High | A | Y | Y | Y | Y | CONFIRMED | Undocumented in README. Safety interlock — must not regress in any future model edit.
REQ-SW-020 | Gearbox | Gear Box, system_729 | The system shall select Reverse, Neutral, or Forward gear from the Car Gears analog input using three input bands. | CarON/OFF = 1; CarGears (analog) = 0-1023 | Gear (signed) = -1 (Backward), 0 (Neutral), or 1 (Forward) per the LOCKED band definition (see Open Decision #1) | ratio=ROUND(CarGears/511.5); ratio=0->Neutral(0); ratio=1->Forward(1); ratio=2->Backward(-1). Breakpoints at 255.75 and 767.25. | High | A | Y | Y | Y | Y | DISCREPANCY - NEEDS DECISION | README states 0-341=Reverse,341-682=Neutral,682-1023=Forward. As-built breakpoints and R/N/F order both differ. See Open Decision #1 — DO NOT test against either version until locked.
REQ-SW-021 | Gearbox — Output Interface | Root, system_665 | The system shall present the signed Gear value to downstream/hardware consumers as two independent boolean flags. | Gear (signed) = -1, 0, or 1 (output of REQ-SW-020) | ForwardGear (digital) = 1 iff Gear=1, else 0. BackwardGear (digital) = 1 iff Gear=-1, else 0. | ForwardGear = (Gear>=1) ? ¦Gear¦ : 0 (Switch, Threshold=1); BackwardGear = (Gear==-1) | Medium | B | Y | Y | Y | Y | CONFIRMED
REQ-SW-030 | Acceleration / Braking — Override | Accel & Brake, system_700 | WHEN Car Brake Paddle <= 200, the system shall zero the acceleration output, overriding the accelerator. | CarBrakePaddle (analog) = 0-1023; CarAccelerationPaddle (analog) = 0-1023 (any value) | carAcceleration = 0, when CarBrakePaddle <= 200 (regardless of accelerator position) | carAcceleration = RelOp(CarBreakPaddle<=200) gates Product3 to 0 when TRUE | High | A | Y | Y | Y | Y | CONFIRMED | Threshold 200 confirmed from 'min torq for break' constant.
REQ-SW-031 | Acceleration — Scaling | Accel & Brake, system_700 | WHEN Car Brake Paddle > 200, the system shall scale the accelerator paddle to an integer output range. | CarBrakePaddle > 200; CarAccelerationPaddle (analog) = 0-1023 | carAcceleration (integer) = 0 to 20 per the LOCKED range definition (see Open Decision #2) | carAcceleration = FLOOR(CarAccelerationPaddle / 51.15), where 51.15 = 1023 / 'forward max speed'(=20) | Medium | B | Y | Y | Y | Y | DISCREPANCY - NEEDS DECISION | README documents 0-100. As-built max is mathematically 20. See Open Decision #2.
REQ-SW-040 | Engine Speed | Engine, system_713 | The system shall compute engine speed as a function of Gear Gain, Acceleration and Hand Brake, clamped to a non-negative value. | GearGain = -1, 0, or 1 (from REQ-SW-020); carAcceleration = 0-20 (from REQ-SW-031); CarHandBreak = 0 or 1 | engineSpeed (analog) = 5 * MAX(GearGain*(carAcceleration - 10*CarHandBreak), 0); i.e. >= 0, no verified upper bound | engineSpeed = Gain1(5) * Switch1[MinMax('Max')(Subtract,0), GearGain, MinMax('Min'->overridden to max)(Subtract,0)] | High | A | Y | Y | Y | Y | CONFIRMED - WITH DEFECT | DEFECT: block named 'Min' has Function overridden to 'max', making it identical to the 'Max' block. Switch1 then selects between two IDENTICAL branches (no-op). Net effect: NO upper saturation exists on engine speed despite the visual Max/Min/Switch structure implying one was intended. See Open Decision #7.
REQ-SW-041 | Engine Speed — Hand Brake Effect | Engine, system_713 | WHEN Hand Brake = 1, the system shall reduce engine speed proportionally to Gear Gain times a fixed factor. | CarHandBreak = 1; GearGain = -1, 0, or 1; carAcceleration = 0-20 | engineSpeed reduced toward 0 relative to the no-handbrake case, per REQ-SW-040 formula with the 10x subtraction term active | Subtraction term = GearGain * 10 * CarHandBreak (10 = 'max speed for hand brake' constant) | High | A | Y | Y | Y | Y | CONFIRMED
REQ-SW-042 | Engine Speed — Ramp Behavior | Engine, system_713 | Hand-brake-induced speed reduction shall occur gradually (ramped), not as an instantaneous step. | CarHandBreak transitions 0 -> 1 while GearGain != 0 and carAcceleration > 0 | engineSpeed shall decrease over a defined non-zero time interval, not within a single simulation step | As-built: instantaneous algebraic subtraction; NO Rate Limiter block found anywhere in the traced chain | Low | C | Y | Y | Y | Y | DISCREPANCY - NEEDS DECISION | README implies 'gradual'. As-built is an immediate step. See Open Decision #3.
REQ-SW-050 | Hand Brake Warning | Engine + Root | WHEN Hand Brake = 1, the system shall assert the Hand Brake Light Warning output. | CarHandBreak = 0 or 1 | HandBreakLightWarning (digital) = same value as CarHandBreak input | HandBreakLightWarning = CarHandBreak passthrough at 'system' subsystem boundary | Medium | B | Y | Y | Y | Y | CONFIRMED
REQ-SW-060 | Steering — Pre-Conversion | Steering, system_682 | The system shall convert the raw steering input into a centered, quantized intermediate value. | SteeringAngle (raw analog) = 0-1025 | signalConvOut (intermediate) = approx -216 to +144, in discrete steps of 72 | signalConvOut = 72 * FLOOR(0.0049*SteeringAngle - 2.5) | High | A | Y | Y | Y | Y | CONFIRMED - AS BUILT | Genuinely coarse: double-floor quantization yields only ~6 discrete output levels across the full input range.
REQ-SW-061 | Steering — Final Wheel Angle | Steering, system_743 | The system shall convert the intermediate steering signal into a final wheel angle in degrees, symmetric about 0 within a documented limit. | signalConvOut (intermediate, from REQ-SW-060) | WheelAngle (deg) = -27.8 to +27.8, symmetric, per the LOCKED specification (see Open Decision #4) | WheelAngle = FLOOR(0.155 * signalConvOut); AS-BUILT combined range is approx -34 deg to +22 deg, asymmetric | High | A | Y | Y | Y | Y | BUG / SAFETY-RELEVANT - NEEDS DECISION | SAFETY: as-built range is asymmetric and does not match the documented +-27.8 deg symmetric limit. MUST be resolved before any HIL run driving a physical steering actuator. See Open Decision #4.
REQ-SW-070 | Indicator — Output Logic | Steering/Indicator, MATLAB Fcn in system_743 | The system shall assert IndicatorLeft iff IndicatorPosition = -1, and IndicatorRight iff IndicatorPosition = 1. | IndicatorPosition (internal) = -1, 0, or 1 nominal | IndicatorLeft, IndicatorRight (digital) each = 0 or 1, mutually exclusive | Extracted verbatim from embedded MATLAB Function block | Medium | B | Y | Y | Y | Y | CONFIRMED
REQ-SW-071 | Indicator — Auto-Cancel | Steering/Indicator, MATLAB Fcn in system_743 | The system shall auto-cancel the active indicator when the steering angle is observed moving in the opposite direction. | IndicatorPosition = 1 (right active) AND steering angle decreasing (turning left); OR IndicatorPosition = -1 (left active) AND steering angle increasing (turning right) | IndicatorPosition transitions to 0 (both indicators OFF) on the qualifying turn-reversal event | if IndicatorPosition==1 and turning==-1 -> IndicatorPosition=0; if IndicatorPosition==-1 and turning==1 -> IndicatorPosition=0 | Medium | B | Y | Y | Y | Y | CONFIRMED - UNDOCUMENTED | Real, working logic with zero mention in the README. Must be locked as an explicit requirement so it can't be silently broken by a future model edit.
REQ-SW-072 | Indicator — Pre-Conversion | Indicator, system_674 | The system shall map the raw Indicator input into Left/Null/Right bands. | Indicator (raw analog) = 0-1023 | IndicatorPosition (internal) = -1 for (0,341], 0 for (341,682], 1 for (682,1023] per the LOCKED band definition (see Open Decision #5) | IndicatorPosition_raw = CEIL(Indicator/341) - 2 | High | A | Y | Y | Y | Y | BUG - BOUNDARY DEFECT | At Indicator EXACTLY 0, CEIL(0/341)=0, giving IndicatorPosition_raw = -2, an out-of-spec value outside {-1,0,1}. Unhandled boundary at the input's minimum. See Open Decision #5.
REQ-SW-073 | Indicator — Blink | README only — not implemented in model | The indicator outputs shall blink at a defined rate when active. | IndicatorLeft = 1 or IndicatorRight = 1, sustained over time | Output shall toggle 0/1 at a fixed rate while active (NOT currently modeled — static level only) | No blink/toggle/oscillator logic found anywhere in the traced subsystems | Low | C | N/A | N/A | N/A | Y (if implemented externally) | DISCREPANCY - NEEDS DECISION | Either out of scope for this model (implemented in Arduino firmware) or missing. See Open Decision #6.
REQ-SW-080 | Hardware Output Scaling | Root, system_660 / 665 / 816 | All root-level outputs destined for the physical/HIL interface shall be scaled by a single, documented conversion factor per channel. | engineSpeed (from REQ-SW-040); WheelAngle (from REQ-SW-061); all other root outputs | Hardware-scaled equivalents delivered to the SCALEXIO/ControlDesk I/O layer, each channel individually gained by 5 in system_816's final stage | EngineSpeed chain: ¦x¦*2.55, then *(1/51), FLOOR, then *5 (system_816 Gain2..Gain7, all =5) | Low | C | N/A | N/A | Y | Y | DISCREPANCY / NEEDS CLEANUP | Scaling is spread across 3 subsystems with no comment explaining the combined constant. Recommend consolidating per channel. See Open Decision #7 (related note).

## 2. MIL Test Spec
MIL Test Spec — Test Specification
STAGE DEFINITION: Model-in-the-Loop. Tests the Simulink MODEL ITSELF on a host PC. No code generation, no target hardware, no real-time constraint. This is the fastest, cheapest stage and should catch every LOGIC error before code generation begins.
Test ID | REQ-ID(s) | Test Objective | INPUT (what you provide) | EXPECTED OUTPUT (what you must observe) | Tool / Environment | Interface | Pass Criteria | Status
MIL-001 | REQ-SW-010 | Ignition LED passthrough - ON | CarON/OFF=1; all other inputs=0 | Car ON/OFF LED = 1 | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-002 | REQ-SW-010 | Ignition LED passthrough - OFF | CarON/OFF=0; all other inputs=0 | Car ON/OFF LED = 0 | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-003 | REQ-SW-011, REQ-SW-020 | Safety interlock: ignition off forces Neutral | CarON/OFF=0; CarGears=1000 (would select Backward if ON) | Gear=0 (Neutral), independent of CarGears value | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-004 | REQ-SW-020 | Gearbox low-band selection | CarON/OFF=1; CarGears=100 (mid of locked Low band) | Gear = LOCKED Low-band value (see Open Decision #1 before running) | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-005 | REQ-SW-020 | Gearbox boundary #1 (as-built 255.75) | CarON/OFF=1; CarGears=255 then CarGears=256 | Gear changes exactly at the LOCKED breakpoint, not before/after | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-006 | REQ-SW-020 | Gearbox boundary #2 (as-built 767.25) | CarON/OFF=1; CarGears=767 then CarGears=768 | Gear changes exactly at the LOCKED breakpoint, not before/after | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-007 | REQ-SW-020 | Gearbox max input | CarON/OFF=1; CarGears=1023 (max) | Gear = LOCKED High-band value, no overflow/clamp error | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-008 | REQ-SW-021 | Forward/Backward flag mapping - Forward | Gear=1 (from REQ-SW-020) | ForwardGear=1, BackwardGear=0 | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-009 | REQ-SW-021 | Forward/Backward flag mapping - Backward | Gear=-1 (from REQ-SW-020) | ForwardGear=0, BackwardGear=1 | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-010 | REQ-SW-030 | Brake override at max accelerator | CarBrakePaddle=201; CarAccelerationPaddle=1023 | carAcceleration = 0 (braking wins) | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-011 | REQ-SW-030 | Brake override boundary | CarBrakePaddle=200 then CarBrakePaddle=201; CarAccelerationPaddle=1023 | carAcceleration=0 at Brake<=200; carAcceleration>0 at Brake=201 | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-012 | REQ-SW-031 | Acceleration scaling at max input | CarBrakePaddle=1023 (not braking); CarAccelerationPaddle=1023 | carAcceleration = 20 (confirms 0-20 range, NOT 0-100) | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-013 | REQ-SW-031 | Acceleration scaling sweep | CarBrakePaddle=1023; CarAccelerationPaddle swept 0,1,50,511,1022,1023 | Output follows FLOOR(Accel/51.15) at every sample point | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-014 | REQ-SW-040 | Engine speed nominal | GearGain=1; carAcceleration=20; CarHandBreak=0 | engineSpeed = 5*MAX(20,0) = 100 | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-015 | REQ-SW-040, REQ-SW-041 | Engine speed with hand brake override | GearGain=1; carAcceleration=5; CarHandBreak=1 | engineSpeed = 5*MAX(5-10,0) = 0 | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-016 | REQ-SW-040 | Engine speed defect confirmation (reverse gear) | GearGain=-1; carAcceleration=20; CarHandBreak=0 | engineSpeed = 5*MAX(-20,0) = 0 — confirms formula behavior; flag if unintended | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-017 | REQ-SW-050 | Hand brake warning light | CarHandBreak=1 | HandBreakLightWarning = 1 | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-018 | REQ-SW-060, REQ-SW-061 | Steering minimum input (safety boundary) | SteeringAngle=0 (minimum) | WheelAngle per as-built formula (~ -34 deg); flag if outside actuator's physical limit | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-019 | REQ-SW-060, REQ-SW-061 | Steering maximum input (safety boundary) | SteeringAngle=1025 (maximum) | WheelAngle per as-built formula (~ +22 deg); confirm asymmetry acceptable or must be fixed | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-020 | REQ-SW-060, REQ-SW-061 | Steering full sweep | SteeringAngle swept 0 to 1025 in steps of 10 | Output only takes the ~6 discrete levels predicted by the formula, no unexpected intermediate values | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-021 | REQ-SW-070, REQ-SW-072 | Indicator boundary defect at zero | Indicator=0 (exact minimum) | Raw IndicatorPosition = -2 (out of {-1,0,1} spec) — FAIL expected until REQ-SW-072 defect is fixed | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-022 | REQ-SW-070 | Indicator nominal - Left band | Indicator=170 (mid of Left band) | IndicatorLeft=1, IndicatorRight=0 | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started
MIL-023 | REQ-SW-071 | Indicator auto-cancel on turn reversal | IndicatorRight active; steering angle sequence: increasing then decreasing | IndicatorRight transitions 1 -> 0 at the point of turn reversal | MATLAB/Simulink, sim() or Simulink Test harness on host PC — no code generation, no target hardware | Direct signal injection into model Inports (Signal Builder / Test Sequence block / script-driven sim()) | Simulink Data Inspector logged output matches EXPECTED OUTPUT within simulation numerical tolerance (exact match expected for integer logic; ±1e-6 for continuous math) | Not Started

## 3. SIL Test Spec
SIL Test Spec — Test Specification
STAGE DEFINITION: Software-in-the-Loop. Tests the AUTO-GENERATED C CODE, compiled and executed on a host PC (still no target hardware). Re-runs the identical MIL input vectors and performs a BACK-TO-BACK comparison against the MIL expected output to catch code-generation, rounding, and integer-overflow defects that MIL cannot see.
Test ID | REQ-ID(s) | Test Objective | INPUT (what you provide) | EXPECTED OUTPUT (what you must observe) | Tool / Environment | Code Under Test | Pass Criteria | Status
SIL-001 | REQ-SW-010 | Ignition LED passthrough - ON | CarON/OFF=1; all other inputs=0 | Car ON/OFF LED = 1 | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-002 | REQ-SW-010 | Ignition LED passthrough - OFF | CarON/OFF=0; all other inputs=0 | Car ON/OFF LED = 0 | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-003 | REQ-SW-011, REQ-SW-020 | Safety interlock: ignition off forces Neutral | CarON/OFF=0; CarGears=1000 (would select Backward if ON) | Gear=0 (Neutral), independent of CarGears value | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-004 | REQ-SW-020 | Gearbox low-band selection | CarON/OFF=1; CarGears=100 (mid of locked Low band) | Gear = LOCKED Low-band value (see Open Decision #1 before running) | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-005 | REQ-SW-020 | Gearbox boundary #1 (as-built 255.75) | CarON/OFF=1; CarGears=255 then CarGears=256 | Gear changes exactly at the LOCKED breakpoint, not before/after | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-006 | REQ-SW-020 | Gearbox boundary #2 (as-built 767.25) | CarON/OFF=1; CarGears=767 then CarGears=768 | Gear changes exactly at the LOCKED breakpoint, not before/after | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-007 | REQ-SW-020 | Gearbox max input | CarON/OFF=1; CarGears=1023 (max) | Gear = LOCKED High-band value, no overflow/clamp error | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-008 | REQ-SW-021 | Forward/Backward flag mapping - Forward | Gear=1 (from REQ-SW-020) | ForwardGear=1, BackwardGear=0 | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-009 | REQ-SW-021 | Forward/Backward flag mapping - Backward | Gear=-1 (from REQ-SW-020) | ForwardGear=0, BackwardGear=1 | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-010 | REQ-SW-030 | Brake override at max accelerator | CarBrakePaddle=201; CarAccelerationPaddle=1023 | carAcceleration = 0 (braking wins) | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-011 | REQ-SW-030 | Brake override boundary | CarBrakePaddle=200 then CarBrakePaddle=201; CarAccelerationPaddle=1023 | carAcceleration=0 at Brake<=200; carAcceleration>0 at Brake=201 | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-012 | REQ-SW-031 | Acceleration scaling at max input | CarBrakePaddle=1023 (not braking); CarAccelerationPaddle=1023 | carAcceleration = 20 (confirms 0-20 range, NOT 0-100) | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-013 | REQ-SW-031 | Acceleration scaling sweep | CarBrakePaddle=1023; CarAccelerationPaddle swept 0,1,50,511,1022,1023 | Output follows FLOOR(Accel/51.15) at every sample point | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-014 | REQ-SW-040 | Engine speed nominal | GearGain=1; carAcceleration=20; CarHandBreak=0 | engineSpeed = 5*MAX(20,0) = 100 | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-015 | REQ-SW-040, REQ-SW-041 | Engine speed with hand brake override | GearGain=1; carAcceleration=5; CarHandBreak=1 | engineSpeed = 5*MAX(5-10,0) = 0 | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-016 | REQ-SW-040 | Engine speed defect confirmation (reverse gear) | GearGain=-1; carAcceleration=20; CarHandBreak=0 | engineSpeed = 5*MAX(-20,0) = 0 — confirms formula behavior; flag if unintended | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-017 | REQ-SW-050 | Hand brake warning light | CarHandBreak=1 | HandBreakLightWarning = 1 | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-018 | REQ-SW-060, REQ-SW-061 | Steering minimum input (safety boundary) | SteeringAngle=0 (minimum) | WheelAngle per as-built formula (~ -34 deg); flag if outside actuator's physical limit | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-019 | REQ-SW-060, REQ-SW-061 | Steering maximum input (safety boundary) | SteeringAngle=1025 (maximum) | WheelAngle per as-built formula (~ +22 deg); confirm asymmetry acceptable or must be fixed | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-020 | REQ-SW-060, REQ-SW-061 | Steering full sweep | SteeringAngle swept 0 to 1025 in steps of 10 | Output only takes the ~6 discrete levels predicted by the formula, no unexpected intermediate values | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-021 | REQ-SW-070, REQ-SW-072 | Indicator boundary defect at zero | Indicator=0 (exact minimum) | Raw IndicatorPosition = -2 (out of {-1,0,1} spec) — FAIL expected until REQ-SW-072 defect is fixed | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-022 | REQ-SW-070 | Indicator nominal - Left band | Indicator=170 (mid of Left band) | IndicatorLeft=1, IndicatorRight=0 | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started
SIL-023 | REQ-SW-071 | Indicator auto-cancel on turn reversal | IndicatorRight active; steering angle sequence: increasing then decreasing | IndicatorRight transitions 1 -> 0 at the point of turn reversal | Embedded Coder / Simulink Coder SIL block, or generated C compiled and run as an S-function on the SAME host PC (not the real-time target) | Auto-generated C code from Veh_Behavior_Modeling_Exp1.slx (post code-gen build) | SIL output matches the corresponding MIL result (back-to-back comparison) within fixed-point/rounding tolerance defined by the code generation data types; any divergence is a code-generation defect, not a logic defect | Not Started

## 4. PIL Test Spec
PIL Test Spec — Test Specification
STAGE DEFINITION: Processor-in-the-Loop. Runs the SAME generated code, cross-compiled for a TARGET-REPRESENTATIVE PROCESSOR (e.g. Raspberry Pi or Jetson AGX Orin ARM core), with I/O delivered over a real communication interface instead of in-memory. Catches compiler-specific and processor-specific defects (rounding, endianness, timing) before committing to the full real-time HIL bench.
Test ID | REQ-ID(s) | Test Objective | INPUT (what you provide) | EXPECTED OUTPUT (what you must observe) | Tool / Environment | Interface | Pass Criteria | Status
PIL-001 | REQ-SW-010 | Ignition LED passthrough - ON | CarON/OFF=1; all other inputs=0 | Car ON/OFF LED = 1 | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-002 | REQ-SW-010 | Ignition LED passthrough - OFF | CarON/OFF=0; all other inputs=0 | Car ON/OFF LED = 0 | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-003 | REQ-SW-011, REQ-SW-020 | Safety interlock: ignition off forces Neutral | CarON/OFF=0; CarGears=1000 (would select Backward if ON) | Gear=0 (Neutral), independent of CarGears value | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-004 | REQ-SW-020 | Gearbox low-band selection | CarON/OFF=1; CarGears=100 (mid of locked Low band) | Gear = LOCKED Low-band value (see Open Decision #1 before running) | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-005 | REQ-SW-020 | Gearbox boundary #1 (as-built 255.75) | CarON/OFF=1; CarGears=255 then CarGears=256 | Gear changes exactly at the LOCKED breakpoint, not before/after | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-006 | REQ-SW-020 | Gearbox boundary #2 (as-built 767.25) | CarON/OFF=1; CarGears=767 then CarGears=768 | Gear changes exactly at the LOCKED breakpoint, not before/after | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-007 | REQ-SW-020 | Gearbox max input | CarON/OFF=1; CarGears=1023 (max) | Gear = LOCKED High-band value, no overflow/clamp error | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-008 | REQ-SW-021 | Forward/Backward flag mapping - Forward | Gear=1 (from REQ-SW-020) | ForwardGear=1, BackwardGear=0 | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-009 | REQ-SW-021 | Forward/Backward flag mapping - Backward | Gear=-1 (from REQ-SW-020) | ForwardGear=0, BackwardGear=1 | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-010 | REQ-SW-030 | Brake override at max accelerator | CarBrakePaddle=201; CarAccelerationPaddle=1023 | carAcceleration = 0 (braking wins) | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-011 | REQ-SW-030 | Brake override boundary | CarBrakePaddle=200 then CarBrakePaddle=201; CarAccelerationPaddle=1023 | carAcceleration=0 at Brake<=200; carAcceleration>0 at Brake=201 | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-012 | REQ-SW-031 | Acceleration scaling at max input | CarBrakePaddle=1023 (not braking); CarAccelerationPaddle=1023 | carAcceleration = 20 (confirms 0-20 range, NOT 0-100) | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-013 | REQ-SW-031 | Acceleration scaling sweep | CarBrakePaddle=1023; CarAccelerationPaddle swept 0,1,50,511,1022,1023 | Output follows FLOOR(Accel/51.15) at every sample point | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-014 | REQ-SW-040 | Engine speed nominal | GearGain=1; carAcceleration=20; CarHandBreak=0 | engineSpeed = 5*MAX(20,0) = 100 | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-015 | REQ-SW-040, REQ-SW-041 | Engine speed with hand brake override | GearGain=1; carAcceleration=5; CarHandBreak=1 | engineSpeed = 5*MAX(5-10,0) = 0 | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-016 | REQ-SW-040 | Engine speed defect confirmation (reverse gear) | GearGain=-1; carAcceleration=20; CarHandBreak=0 | engineSpeed = 5*MAX(-20,0) = 0 — confirms formula behavior; flag if unintended | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-017 | REQ-SW-050 | Hand brake warning light | CarHandBreak=1 | HandBreakLightWarning = 1 | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-018 | REQ-SW-060, REQ-SW-061 | Steering minimum input (safety boundary) | SteeringAngle=0 (minimum) | WheelAngle per as-built formula (~ -34 deg); flag if outside actuator's physical limit | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-019 | REQ-SW-060, REQ-SW-061 | Steering maximum input (safety boundary) | SteeringAngle=1025 (maximum) | WheelAngle per as-built formula (~ +22 deg); confirm asymmetry acceptable or must be fixed | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-020 | REQ-SW-060, REQ-SW-061 | Steering full sweep | SteeringAngle swept 0 to 1025 in steps of 10 | Output only takes the ~6 discrete levels predicted by the formula, no unexpected intermediate values | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-021 | REQ-SW-070, REQ-SW-072 | Indicator boundary defect at zero | Indicator=0 (exact minimum) | Raw IndicatorPosition = -2 (out of {-1,0,1} spec) — FAIL expected until REQ-SW-072 defect is fixed | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-022 | REQ-SW-070 | Indicator nominal - Left band | Indicator=170 (mid of Left band) | IndicatorLeft=1, IndicatorRight=0 | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started
PIL-023 | REQ-SW-071 | Indicator auto-cancel on turn reversal | IndicatorRight active; steering angle sequence: increasing then decreasing | IndicatorRight transitions 1 -> 0 at the point of turn reversal | Target-representative processor (Raspberry Pi / Jetson AGX Orin cross-compile, or dSPACE-supported PIL target) running the cross-compiled generated code | CAN bus, serial/UART, or GPIO — inputs injected via a test harness script over the physical communication interface, not in-memory | PIL output matches the corresponding SIL result within the same tolerance, AND execution timing per test vector is captured and stays within the model's step-size budget (no processor-specific timing violation) | Not Started

## 5. HIL Test Spec
HIL Test Spec — Test Specification
STAGE DEFINITION: Hardware-in-the-Loop. Runs the compiled real-time application ON THE dSPACE SCALEXIO TARGET with REAL electrical I/O to the Arduino ECU stand-in and physical actuators. This is the gold-standard validation stage for this project — the only stage with true real-time determinism and physical hardware in the loop. Script via ControlDesk's Automation API for repeatability; do not rely on manual GUI signal injection.
Test ID | REQ-ID(s) | Test Objective | INPUT (what you provide) | EXPECTED OUTPUT (what you must observe) | Tool / Environment | Physical Interface | Pass Criteria | Status
HIL-001 | REQ-SW-010 | Ignition LED passthrough - ON | CarON/OFF=1; all other inputs=0 | Car ON/OFF LED = 1 | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-002 | REQ-SW-010 | Ignition LED passthrough - OFF | CarON/OFF=0; all other inputs=0 | Car ON/OFF LED = 0 | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-003 | REQ-SW-011, REQ-SW-020 | Safety interlock: ignition off forces Neutral | CarON/OFF=0; CarGears=1000 (would select Backward if ON) | Gear=0 (Neutral), independent of CarGears value | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-004 | REQ-SW-020 | Gearbox low-band selection | CarON/OFF=1; CarGears=100 (mid of locked Low band) | Gear = LOCKED Low-band value (see Open Decision #1 before running) | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-005 | REQ-SW-020 | Gearbox boundary #1 (as-built 255.75) | CarON/OFF=1; CarGears=255 then CarGears=256 | Gear changes exactly at the LOCKED breakpoint, not before/after | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-006 | REQ-SW-020 | Gearbox boundary #2 (as-built 767.25) | CarON/OFF=1; CarGears=767 then CarGears=768 | Gear changes exactly at the LOCKED breakpoint, not before/after | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-007 | REQ-SW-020 | Gearbox max input | CarON/OFF=1; CarGears=1023 (max) | Gear = LOCKED High-band value, no overflow/clamp error | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-008 | REQ-SW-021 | Forward/Backward flag mapping - Forward | Gear=1 (from REQ-SW-020) | ForwardGear=1, BackwardGear=0 | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-009 | REQ-SW-021 | Forward/Backward flag mapping - Backward | Gear=-1 (from REQ-SW-020) | ForwardGear=0, BackwardGear=1 | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-010 | REQ-SW-030 | Brake override at max accelerator | CarBrakePaddle=201; CarAccelerationPaddle=1023 | carAcceleration = 0 (braking wins) | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-011 | REQ-SW-030 | Brake override boundary | CarBrakePaddle=200 then CarBrakePaddle=201; CarAccelerationPaddle=1023 | carAcceleration=0 at Brake<=200; carAcceleration>0 at Brake=201 | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-012 | REQ-SW-031 | Acceleration scaling at max input | CarBrakePaddle=1023 (not braking); CarAccelerationPaddle=1023 | carAcceleration = 20 (confirms 0-20 range, NOT 0-100) | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-013 | REQ-SW-031 | Acceleration scaling sweep | CarBrakePaddle=1023; CarAccelerationPaddle swept 0,1,50,511,1022,1023 | Output follows FLOOR(Accel/51.15) at every sample point | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-014 | REQ-SW-040 | Engine speed nominal | GearGain=1; carAcceleration=20; CarHandBreak=0 | engineSpeed = 5*MAX(20,0) = 100 | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-015 | REQ-SW-040, REQ-SW-041 | Engine speed with hand brake override | GearGain=1; carAcceleration=5; CarHandBreak=1 | engineSpeed = 5*MAX(5-10,0) = 0 | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-016 | REQ-SW-040 | Engine speed defect confirmation (reverse gear) | GearGain=-1; carAcceleration=20; CarHandBreak=0 | engineSpeed = 5*MAX(-20,0) = 0 — confirms formula behavior; flag if unintended | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-017 | REQ-SW-050 | Hand brake warning light | CarHandBreak=1 | HandBreakLightWarning = 1 | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-018 | REQ-SW-060, REQ-SW-061 | Steering minimum input (safety boundary) | SteeringAngle=0 (minimum) | WheelAngle per as-built formula (~ -34 deg); flag if outside actuator's physical limit | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-019 | REQ-SW-060, REQ-SW-061 | Steering maximum input (safety boundary) | SteeringAngle=1025 (maximum) | WheelAngle per as-built formula (~ +22 deg); confirm asymmetry acceptable or must be fixed | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-020 | REQ-SW-060, REQ-SW-061 | Steering full sweep | SteeringAngle swept 0 to 1025 in steps of 10 | Output only takes the ~6 discrete levels predicted by the formula, no unexpected intermediate values | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-021 | REQ-SW-070, REQ-SW-072 | Indicator boundary defect at zero | Indicator=0 (exact minimum) | Raw IndicatorPosition = -2 (out of {-1,0,1} spec) — FAIL expected until REQ-SW-072 defect is fixed | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-022 | REQ-SW-070 | Indicator nominal - Left band | Indicator=170 (mid of Left band) | IndicatorLeft=1, IndicatorRight=0 | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started
HIL-023 | REQ-SW-071 | Indicator auto-cancel on turn reversal | IndicatorRight active; steering angle sequence: increasing then decreasing | IndicatorRight transitions 1 -> 0 at the point of turn reversal | dSPACE SCALEXIO + ControlDesk experiment (.CDE), scripted via ControlDesk Automation/Python API | Real analog/digital I/O per Hardware Topology (.htfx): SCALEXIO I/O -> Arduino Mega ECU stand-in -> physical actuators (servo, LEDs, PWM motor) | Physically measured/logged output (MDF/CSV via ControlDesk) matches the corresponding SIL/PIL result within sensor/actuator tolerance, AND real-time deadline is met on every simulation step (no overrun reported by SCALEXIO) | Not Started

## 6. Traceability Matrix
REQ-ID | Requirement Summary | Safety Class | MIL Test ID(s) | SIL Test ID(s) | PIL Test ID(s) | HIL Test ID(s) | Overall V&V Status
REQ-SW-010 | Ignition LED passthrough | B | MIL-001, 002 | SIL-001, 002 | PIL-001, 002 | HIL-001, 002 | Not Started
REQ-SW-011 | Ignition off forces Neutral (safety interlock) | A | MIL-003 | SIL-003 | PIL-003 | HIL-003 | Not Started
REQ-SW-020 | Gearbox band selection (NEEDS DECISION) | A | MIL-003, 004, 005, 006, 007 | SIL-003, 004, 005, 006, 007 | PIL-003, 004, 005, 006, 007 | HIL-003, 004, 005, 006, 007 | Not Started
REQ-SW-021 | Forward/Backward gear flags | B | MIL-008, 009 | SIL-008, 009 | PIL-008, 009 | HIL-008, 009 | Not Started
REQ-SW-030 | Brake overrides accelerator | A | MIL-010, 011 | SIL-010, 011 | PIL-010, 011 | HIL-010, 011 | Not Started
REQ-SW-031 | Accelerator scaling (NEEDS DECISION) | B | MIL-012, 013 | SIL-012, 013 | PIL-012, 013 | HIL-012, 013 | Not Started
REQ-SW-040 | Engine speed formula (has defect) | A | MIL-014, 015, 016 | SIL-014, 015, 016 | PIL-014, 015, 016 | HIL-014, 015, 016 | Not Started
REQ-SW-041 | Hand brake reduces engine speed | A | MIL-015 | SIL-015 | PIL-015 | HIL-015 | Not Started
REQ-SW-042 | Hand brake ramp behavior (NEEDS DECISION) | C | TBD | TBD | TBD | TBD | Not Started
REQ-SW-050 | Hand brake warning light | B | MIL-017 | SIL-017 | PIL-017 | HIL-017 | Not Started
REQ-SW-060 | Steering pre-conversion / quantization | A | MIL-018, 019, 020 | SIL-018, 019, 020 | PIL-018, 019, 020 | HIL-018, 019, 020 | Not Started
REQ-SW-061 | Final wheel angle (asymmetric — SAFETY, NEEDS DECISION) | A | MIL-018, 019, 020 | SIL-018, 019, 020 | PIL-018, 019, 020 | HIL-018, 019, 020 | Not Started
REQ-SW-070 | Indicator level logic | B | MIL-021, 022 | SIL-021, 022 | PIL-021, 022 | HIL-021, 022 | Not Started
REQ-SW-071 | Indicator auto-cancel | B | MIL-023 | SIL-023 | PIL-023 | HIL-023 | Not Started
REQ-SW-072 | Indicator boundary defect at input=0 | A | MIL-021 | SIL-021 | PIL-021 | HIL-021 | Not Started
REQ-SW-073 | Blink behavior (NEEDS DECISION) | C | TBD | TBD | TBD | TBD | Not Started
REQ-SW-080 | Hardware output scaling consolidation | C | TBD | TBD | TBD | TBD | Not Started

## 7. Open Decisions
# | REQ-ID | Decision Needed | Option A (README) | Option B (As-Built Model) | Recommendation | Decided? | Decided Value
1 | REQ-SW-020 | Which gear-threshold/mapping is correct? | 0-341=Rev, 341-682=Neutral, 682-1023=Fwd | 0-255.75=Neutral, 255.75-767.25=Fwd, 767.25-1023=Backward | Pick ONE and update either the README or the model to match. Do not test or ship with both versions live. | N
2 | REQ-SW-031 | Is the acceleration output range 0-100 or 0-20? | 0-100 (README) | 0-20 (as-built, forced by the 'forward max speed'=20 constant) | If 0-100 is genuinely required, change the constant to 5 or add a x5 gain stage downstream. | N
3 | REQ-SW-042 | Should hand-brake speed reduction be instantaneous or ramped? | 'Gradual' (README) | Instantaneous step (as-built, no Rate Limiter present) | If gradual is required, add a Rate Limiter block on the engine-speed path when HandBrake transitions 0->1. | N
4 | REQ-SW-061 | Should steering output be symmetric +-27.8 deg, or is the as-built asymmetric range acceptable? | +-27.8 deg symmetric (README) | approx -34 deg to +22 deg, asymmetric and quantized (as-built) | SAFETY-RELEVANT. Resolve before any HIL run with a physical steering actuator. Re-derive the gain chain to hit the documented symmetric range, or formally update the spec. | N
5 | REQ-SW-072 | How should Indicator input = 0 exactly be handled? | Not addressed in README | Produces out-of-spec value -2 (as-built bug) | Clamp CEIL()-2 output to {-1,0,1}, or redefine the band to explicitly include 0 in the Left band. | N
6 | REQ-SW-073 | Is blinking in scope for this model, or a hardware/firmware concern? | Blink implied (README) | No blink/oscillator logic found in the model | If required at SIL/PIL fidelity, add a toggle block driven by a fixed-frequency pulse generator; otherwise document that it's an Arduino-side concern. | N
7 | REQ-SW-040 | Is the Max/Min/Switch1 redundancy intentional or a leftover bug? | Not documented either way | Switch1 currently has no effect — both data inputs identical (MAX(x,0)) | If an upper saturation on engine speed was intended, restore the 'Min' block's Function to 'min' and supply the real upper-bound constant. If not, remove the dead structure. | N

## 8. HW Integration Targets
Where each target platform fits in the MIL -> SIL -> PIL -> HIL chain for THIS project
Platform | V-Cycle Stage | Role in this project | How it connects | What it validates | Practical notes
PC (host workstation) | MIL + SIL | Runs the Simulink model directly (MIL) and the auto-generated C code as a host-compiled SIL build. | N/A — pure software. | Model logic correctness (MIL) and code-generation fidelity vs the model (SIL back-to-back). | Do this first. Cheapest, fastest, highest test-vector throughput.
Raspberry Pi 4/5 | PIL / early HIL substitute | Cross-compiled generated code run as a PIL target over CAN-HAT/GPIO; early bring-up before SCALEXIO bench access. | USB-CAN adapter or MCP2515 CAN HAT; GPIO/PWM for stand-in signals; SSH/serial for harness control. | Compiler/OS-scheduling-specific timing and rounding differences ahead of full HIL. | Standard Linux, not hard-real-time — indicative PIL smoke test only, not a HIL replacement.
Arduino Mega 2560 | HIL peripheral / ECU stand-in | Already used in this repo as the prototype ECU driving physical actuators (servo, LEDs, PWM motor). | Serial/digital/analog wired to SCALEXIO I/O per the existing .htfx mapping. | Physical hardware-software handshake with real (non-ideal) voltages/timing. | Keep scoped to actuator/sensor emulation — not a PIL target for the full controller.
Jetson AGX Orin | PIL (representative embedded target) | Cross-compile and run generated code on ARM cores with a real-time-capable kernel, closer to a real ECU's compute profile than a Pi. | CAN (onboard controller or USB-CAN); GPIO/I2C/SPI for sensor emulation; Ethernet for harness control. | Real ARM rounding/timing behavior, multi-threaded scheduling, mixed AI+control workloads. | Overkill for the current pure control-logic model; right target if perception/AI gets added alongside the controller (see vehicleController folder).
Jetson Thor | PIL (next-gen representative target) | Same role as Orin at a higher-performance automotive-class compute tier. | Same connectivity approach as Orin. | Same as Orin, higher throughput. | Don't add until there's a concrete compute reason; Orin or even the Pi is sufficient for this control-only model.
dSPACE SCALEXIO + LabBox | HIL (primary bench) | The project's existing real-time HIL target — what ConfigurationDesk/.htfx and ControlDesk/.CDE files are already built for. | Already wired per the repo's Hardware Topology files; I/O to Arduino Mega and any added actuators/sensors. | Real-time determinism, true I/O timing, closed-loop behavior with the real dSPACE RTOS. | What the README currently calls 'SIL' actually belongs here — script the ControlDesk experiments via its Python/Automation API for repeatability instead of manual GUI injection.
dSPACE MicroAutoBox III | HIL (deployable / in-vehicle) | Compact, deployable dSPACE target for moving from bench HIL to an in-vehicle or mobile-rig stage (e.g. the Skateboard EV in vehicleController). | Same ConfigurationDesk/.htfx workflow; CAN and I/O to real vehicle actuators instead of the Arduino stand-in. | Full vehicle-integration-level behavior with real motor controller, real CAN bus, real dynamics. | Natural next step once SCALEXIO bench HIL is fully passing.